## Sheet1
Consultancy Project & Practicum (DataMicron Sdn Bhd)
Title : Time Series Prediction of Real Private Consumption for Future Demand
No. | Tasks | 2020 | [11 empty] | 2021
|  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
1 | Introduction
1.1 | Online meeting with client for problem understanding | bar: October W1
1.2 | Write-up on Problem Background, Statement, Objectives, and Project Scope | bar: October W1 to October W2
2 | Literature Review
2.1 | Review on the timeline of RPC Forecasting in literatures. | bar: October W2 to December W9
2.2 | Survey on published RPC Time Series and Forecasting methods | bar: October W2 to December W9
2.3 | Compare available analytical tools for data science tasks | bar: October W2 to December W9
3 | Methodology
3.1 | Collect data and its descriptions | bar: October W1 to October W4
3.2 | Design the project framework | bar: November W5 to December W9
3.3 | Define steps and parameters in constructing Random Forest, and Support Vector Machine models | bar: November W6 to January W16
3.4 | Prepare presentation slides for CDS590 mid-term presentation | bar: November W7 to November W8
CDS590 mid-term presentation | bar: December W9
4 | Results and Discussions
4.1 | Compare performances between machine learning models | bar: November W8 to January W16
4.2 | Optimise forecasting parameters for machine learning models | bar: November W8 to January W16
4.3 | Distinguish prediction performance between statistical and machine learning models | bar: November W8 to January W16
4.4 | Forecast Real Private Consumption using the best machine learning model for the Quarter 2, 2020 | bar: January W15 to January W16
5 | Conclusion
5.1 | Overall summary of the project | bar: January W15 to February W17
5.2 | Finish the project write-up | bar: October W2 to February W18
6 | Presentation and Submission
6.1 | Prepare slides for CSMinD 2021 | bar: February W17 to February W18
CSMinD 2021 | bar: February W18
6.2 | Submit the project report to USM | bar: February W18